## Working List
Date | Area | Big Goals | Problem | Priority | Explanation | Plan | Time Frame (Months) | Percent complete | Date completed | Notes
2020-12-29 | Camp Petrel | Big | Remove Old Asbestos Toilets, Replace with better toilets Camp Petrel Side | 1 | Safety, Eyesore | Grants, Gary Murray has a quote for demolition, need to chase down Grants | 60 | 10% |  | Quoted, with Joan UQ potential grant?
2022-04-21 | Camp Petrel |  | New Toilet Block | 1 | Complaince For Scouts, Individual Showers Etc | Grants | 48 | 0%
2020-12-29 | Camp Petrel |  | Toilet Block Stairs. | 1 | Required for Safety |  | 3 | 0%
2020-12-29 | Camp Petrel |  | Dorms | 1 | Fix Ramp into Dorms |  | 3 | 0%
2020-12-29 | Seeonee |  | Clean Up Random Metal | 1 | Safety | Working Bees | 6 | 50% |  | ongoing
2020-12-29 | Seeonee |  | Equipment log books | 1 | urgently required as part of training | Scott | 2 | 50%
2020-12-29 | Seeonee |  | Fix Front Fence | 1 | The Front Fence Near The Gate Is Damaged\Not Existent | Working Bees | 3 | 50% |  | bolders to fix fence
2020-12-29 | Seeonee |  | Organise contractor to quote compliance for all buildings | 1 | Check\Install fire extinguishers etc |  | 2 | 10% |  | Organised a contrator Buddy's to give a quote
2020-12-29 | Seeonee |  | Purchase fire equiupment | 1 | Need a portable fire system trailer\pump pod |  | 3 | 10% |  | Applied for Grant waiting response
2020-12-29 | Seeonee |  | Fire perparedness | 1 | Audit the park for fire preparedness |  | 1 | 0%
2020-12-29 | Seeonee |  | Emergecy Evacuation Plans | 1 |  |  | 2 | 0%
2020-12-29 | Brown Hut |  | Fix Hot Water | 2 | Not Working At The Moment | Fundraising, Grants | 6 | 20% |  | have quote for gas work, wollom construction looking at this
2020-12-29 | Brown Hut |  | Fix Door | 2 | Door Jams When Opened Near The Water Tank | Working Bees | 6 | 0% |  | Fixed???
2020-12-29 | Brown hut |  | Fix Toilet door | 2 | needed repairs. Remove urinal\board up. |  | 2 | 0%
2020-12-29 | Brown hut toilets |  | Signage | 2 | How To Use The Facilities And Who To Contact | In Progress (Scott Neill) | 3 | 60% |  | WIP
2020-12-29 | Camp Petrel |  | Dorms | 2 | Paint and repair insides of dorms |  | 3 | 0%
2020-12-29 | Camp Petrel |  | Dorms Facelift | 2 | Presentation | Grants\Fundraising Working Bees | 48 | 0%
2020-12-29 | Camp Petrel |  | Solar Panels | 2 | Save On Power For Cold Room Etc… | Grant | 24 | 0% |  | Apply for grants
2020-12-29 | Picnic area |  | Clean General Area | 2 | Presentation | Working Bees | 18 | 0%
2020-12-29 | Picnic area |  | Remove All Rubbish | 2 | Presentation | Working Bees | 18 | 0%
2020-12-29 | Seeonee |  | Creek Crossing | 2 | Clean Up The Bank Around The Bridge, Open It Up For Safety | Working Bees | 6 | 50% |  | Telstra maintenance underway 22/3
2020-12-29 | Seeonee |  | Tractor User Training | 2 | Risk Mitigation | Dwayne Kersey\Gary Muhling | 3 | 40%
2020-12-29 | Seeonee |  | New Tractor | 2 | Replace And Upgrade Tractor | Grant | 12 | 5% |  | Quoted, waiting for Grant
2020-12-29 | Seeonee |  | Fix Trailer Floor | 2 | Safety And To Be Able To Use It Around The Park | Funds | 6 | 0%
2020-12-29 | Seeonee |  | Repair Weir | 2 | Huge Asset To Seeonee, Big Risk | Contact Army Engineers? Contact Concrete Companies, Possible Side Project. | 24 | 0% |  | Potentially K and T Daley will repair
2020-12-29 | Seeonee |  | Workshop Shed | 2 | Some Where To Lock Up All The Equipment And Work On It Safely. | Grants | 48 | 0%
2020-12-29 | Arunga Shed |  | Solar Trickle Charger For Tractor Location. | 3 | Keep The Batteries Charged | Install Solar charger | 24 | 10%
2020-12-29 | Arunga Shed |  | Power Points Outside The Shed. | 3 | Keep People Outside Of The Locked Area. | Chase Quote From Electrican To Move Power Points External | 12 | 0%
2020-12-29 | Camp Petrel |  | Kitchen Upgrades | 3 | Upgrade The Kitchen Standard, Look At Commercial Possibility | Chase Quote\Grants | 36 | 0%
2021-12-29 | Camp Petrel |  | Paint The Inside | 3 | Appearance | Fundraising? Working Bee? | 24 | 0%
2020-12-29 | Camp Petrel |  | Paint The Outside | 3 | Appearance | Fundraising? Working Bee? | 24 | 0%
2020-12-29 | Obstacle |  | Finish First One | 3 | Unused And Unfinished At The Moment | Clean The Area, Working Bee? Auger Bit On Tractor? | 60 | 30%
2020-12-29 | Obstacle |  | Build Second One | 3 | To Have 2 Courses | Grant? Fundraising? Working Bee | 60 | 0%
2020-12-29 | Obstacle |  | Install Abseil Tower | 3 | On Site Abseiling And Climbing Wall. | Grants | 60 | 0%
2020-12-29 | Obstacle |  | Power | 3 | To Make A Proper Adventure Zone | Grants | 60 | 0%
2020-12-29 | Obstacle |  | Toilets | 3 | To Make A Proper Adventure Zone | Grants | 60 | 0%
2020-12-29 | Obstacle |  | Water | 3 | To Make A Proper Adventure Zone | Grants | 60 | 0%
2020-12-29 | Picnic area |  | Lights | 3 | To Make The Area Useable | Hire Ewp, Need Funds, Have Electrician | 36 | 0%
2020-12-29 | Picnic area |  | Log Seats At The Camp Fire | 3 | Presentation | Use The Logs On The Corner Near Camp Petrel Turn Off | 6 | 0%
2020-12-29 | Picnic area |  | Power | 3 | To Make The Area Useable | Hire Ewp, Need Funds, Have Electrician | 36 | 0%
2020-12-29 | Picnic area |  | Repair Old Tables | 3 | To Make The Area Useable | Working Bees | 36 | 0%
2020-12-29 | Scouts Chapel |  | Rope Fence? | 3 | Presentation | Working Bees\Rovers? | 36 | 0%
2020-12-29 | Seeonee |  | Stump Removal | 3 | Gradually Remove All Stumps In Common Areas | Working Bees | 36 | 50% |  | Tristan has burn offs
2020-12-29 | Seeonee |  | Burn Off | 3 | Organise A Burn Off Schedule With The Rural Fire Brigade | Committees | 24 | 30% |  | Waiting for cooler months, was pushed back due to COVID
2020-12-29 | Seeonee |  | Sign Before The Turn Off | 3 | Short Notice To Turn Into Seeonee For New Visitors | Sign On The Road, Funds\Time | 18 | 20% |  | Apply for sign, expensive TMR
2020-12-29 | Seeonee |  | School Holiday Programs | 3 | Advertising For Scouts | District Scouts | 48 | 0%
2020-12-29 | Seeonee |  | Zero Turn Mower | 3 | Replacement, Larger | Grant | 36 | 0%
2020-12-29 | Seeonee |  | Bridge | 4 | Replace the creek crossing | grants | 120 | 5% |  | Woolum Constructions looking at this? engineers etc.
2020-12-29 | Seeonee |  | Develop other areas for Camping | 4 | More sites than Brown and Petrel | Working bees | 60 | 0%
2020-12-29 | Seeonee |  | Dorms at Brown Hut | 4 | Bunks at Brown Hut | Grants | 120 | 0%
2020-12-29 | Seeonee |  | Grants to Youth | 4 | Excess income from Seeonee to support youth members | Committees | 120 | 0%
2020-12-29 | Seeonee |  | High Ropes Course | 4 | Increase the activites at Seeonee | Grants | 120 | 0%
2020-12-29 | Seeonee |  | Paid Caretakers | 4 | Part Time Full time? | Committees | 120 | 0%
2020-12-29 | Seeonee |  | Partnerships | 4 | Businesses, Community Groups, to use and further Seeonee | Committees | 60 | 0%
2020-12-29 | Seeonee |  | Partnerships with Schools | 4 | use of seeonee for camps etc | Grants, Committee | 60 | 0%
2020-12-29 | Seeonee |  | Repair all fences around park | 4 | Security | Fundraising\Grants | 60 | 0%
2020-12-29 | Seeonee |  | Training Centre Hall | 4 | Brown Hut Side | Grants | 120 | 0%
2020-12-29 | Seeonee |  | Training Centre Hall | 4 | Camp Petrel Side | Grants | 120 | 0%
2020-12-29 | Seeonee |  | Water | 4 | Connect the main sites to town water | Grants | 120 | 0%
New Dorms

## 5 year Goals
Seeonee Park Goals
New Toilets Camp Petrel
Remove Asbestos toilet block
Bitumen\road base roads
mains water
abseil tower
low ropes cours
high roped

## Completed Lists
| Area | Problem | Priority | Explanation | Plan | Time Frame (Months) | Percent complete
2019 | Rudd hut | Fix The Zero Turn | 1 | Not Working, Wont Start | Chasing Parts, Possible Camshaft Issues | 1 | 100%
2019 | Seeonee | Upgrade to Xero Accounting | 1 | Updated Cashbook, Invoicing and GST recovery | Treasurer | 2 | 100%
2019 | Brown Hut | Clean | 1 | Presentation | Working Bees | 3 | 100%
2019 | Brown Hut | Reorganise | 1 | Presentation | Working Bees | 3 | 100%
2019 | Camp Petrel | Empty Rubbish\Reorganise | 1 | Appearance And Usability | Working Bees | 3 | 100%
2019 | Arunga Shed | Clean Rubbish | 1 | Presentation | Working Bees | 3 | 100%
2019 | Camp Petrel | Fix Computer Room Door | 1 | Security And Appearance | Working Bees | 3 | 100%
2019 | Arunga Shed | Empty Shed | 2 | New Home For Tractor, Presentation | Working Bees | 3 | 100%
2019 | Rudd hut | Service Hydraulics | 2 | No Downwards Force. | Funds | 6 | 100%
2019 | Seeonee | Signs At The Front Gate | 2 | Fix The Laser Skirmish Sign, Tidy The Area | Mark Fewtrell Laser Skirmish To Organise | 3 | 100%
2019 | Seeonee | Register Of Users | 1 | List All Users Who Use The Park | On Going Indefinate | 3 | 100%
2020 | Arunga Shed | Fix Lights | 2 | Some Spot Lights Not Working | Have the parts just need to organise the fix | 3 | 100%
2020 | Brown Hut | Move All The Archive Stuff To Camp Petrel | 2 | Into The Museum | Working Bees | 6 | 100% | compactus installed
2020 | Brown Hut | Install Fans | 3 | To Make It More Friendly In The Hotter Months | Chase Grants? Fundraising? Electrician | 24 | 100% | done
2020 | Brown hut toilets | Clean | 2 | Hygiene | Working Bees | 3 | 100% | ongoing
2020 | Camp Petrel | Stove | 1 | Broken Stove, Only One Working | Fundraising | 3 | 100%
2020 | Camp Petrel | Museum | 2 | Possibly Use One Of The Dorm Rooms To Store All The Archive Images Etc For Scouts In Our District | Requested Discrentionary Funds From The Council | 24 | 100% | moved to brown
2020 | Rudd hut | Solar Charger For Ride On Etc Battery | 2 | Keep The Batteries Charged | Working bee in Rudd First | 2 | 100%
2020 | Scouts Chapel | New Seats | 3 | Current Seats Damaged And Uncomfortable. | Working Bees\Rovers? | 36 | 100%
2020 | Scouts Chapel | Coat Of Paint | 3 | Presentation | Working Bees\Rovers? | 36 | 100%
2020 | Seeonee | User Agreements | 1 | Re Do All The Agreements With People Who Use The Park | On Going Indefinate | 3 | 100%
2020 | Seeonee | User Manual | 1 | Basic User Manual, Key Contacts | In Progress (Scott Neill) | 3 | 100%
2020 | Seeonee | Fellowship | 1 | Increase The Membership Of Fellowship, Possibility To Pay For Membership | District Scouts | 12 | 100% | closed fellowship
2020 | Seeonee | Roof Over Container | 2 | Stop Water Entry, Make The Container Usable | Scrap Sheets To Replace The Roof? | 12 | 100% | Archers fixed this
2020 | Seeonee | Empty And De Mould The Container | 2 | Make The Container Usable | Working Bees | 12 | 100% | Archers fixed this
2020 | Seeonee | Security | 2 | Replace All Locks And Keys | Fundraising | 24 | 100% | combination locks
2020 | Seeonee | Containter Collection Recycling | 3 | Income, Recycling Facilities | Scouts Qld, Scott Neill Dc | 24 | 100% | Lost to Kanga Bins
2020 | Seeonee | Key Register | 1 | Security | In Progress (Scott Neill) | 3 | 100% | removed excess and changed to combination
2020 | Seeonee | Cameras At The Gate | 2 | Keep Track Of Unauthorised Users | Funds | 6 | 100% | installed
2020 | Seeonee | Map Of Park And Signage At Entrance | 3 | High Level Map | Draft Up Design, Fundraise? | 24 | 100% | Installed!
2020 | Seeonee | New Trailer | 3 | To Take Rubbish Away From The Park | Grant? Fundraising? | 24 | 100% | double up
2020 | Seeonee | Speed Signs | 3 | Safety | Fundraising\Grants | 60 | 100% | Installed
2020 | Seeonee | Road Signs | 3 | Safety | Fundraising\Grants | 60 | 100% | Installed
2021 | Seeonee | Trailer | 1 | Assist with maintenance around the Scout Park, rubbish removal etc | Grants | 12 | 100% | Trailer purchased and supplied!!! 22/3/21
2022 | Arunga Shed | Poor light standard | 3 | Lights broken and poor standard | replace | 12 | 100% | 2022-04-01
2022 | Brown Hut | Fix Stoves | 2 | Not Working At The Moment | Fundraising, Grants | 6 | 100% | 2021-11-01 | finished
2022 | Brown Hut | Paint Brown Hut | 2 | Repaint Brown Hut | Woolom Constructions! | 6 | 100% | 2021-06-01 | Paint Donated, waiting for volunteers from Woolum 22/3
2022 | Brown Hut | Toilets | 2 | Replacement Toilets | Grants\Fundraising Working Bees | 60 | 100% | 2021-06-01 | Woolom Construction? potential
2022 | Brown hut toilets | Cleaning And Toilet Paper Storage Location | 2 | Basic Housekeeping | Working Bees | 3 | 100% | 2022-03-01 | look at storage cupboard
2022 | Camp Petrel | Replacement Stove | 1 | Current Stove is hard to use possibly unsafe | Grant | 6 | 100% | 2021-03-01 | Oven supplied needs to be installed
2022 | Camp Petrel | Light around Dorms | 2 | poor lighting | replace | 12 | 100% | 2022-03-01
2022 | Camp Petrel | Replace All Bunks And Matresses | 2 | Chase A Grant To Replace All, Make Compliant | Grants, Committee | 12 | 100% | 2021-03-01 | 33 Bunks bought, waiting to paint the dorms to install!! 22/3
2022 | Rudd hut | Clean\Organise | 1 | Unuseable and unsafe | Working Bee - ongoing | 2 | 100% | 2021-06-01 | ongoing
2022 | Rudd hut | Small Container Use | 1 | Unuseable and unsafe | Working Bee - ongoing | 2 | 100% | 2021-06-01
2022 | Seeonee | Asbestos Register | 1 | Signs and QR codes to go up in all buildings |  | 1 | 100% | 2021-02-01
2022 | Seeonee | Dirt roads | 3 | Seal the roads, speed bumps | Continuous | 60 | 100% | 2022-04-21
2022 | Seeonee | Tooling | 3 | General Tools Manual And Electrical | Grants, Donations | 36 | 100% | 2022-04-21 | toolbox, pressure washer bought
2022-07-02 | Brown hut |  | Connect new toilets to power | 1 | lights and hot water | Electrican | 1 | 100%
2022-07-02 | Brown Hut |  | New Toilet Hot water timer | 2 | Epensive power bills, install 48hr timer | Done | 1 | 100%
2022-07-02 | Camp Petrel |  | Boys Toilet Hot water timer | 2 | Epensive power bills, install 48hr timer | Done | 1 | 100%
2020-12-29 | Camp Petrel |  | Toilet Block Hand Rails - Leaders Toilets | 1 | Required for Safety | Install steps etc | 3 | 100%

## Work Areas
Area
Rudd hut
Camp Petrel
Seeonee
Brown Hut
Arunga Shed
Brown hut toilets
Picnic area
Obstacle
Scouts Chapel

## Standard Suppliers
Standard Suppliers
Name | Contact | What
JJ Kerrs |  | Bins
Norstate |  | Gas

## Hirers
Current Users | Hiring Dates | Agreement | Insurance
Captain De Buch (Re-enactment) | Sundays
Laser Skirmish | As Booked | Yes | Yes
Field Archers | Lease | 3 Years | Yes
CQ Mountain Bikers | 2nd and 3rd Sunday of the month | N\A
Advanced Driver Training | As Booked | N\A
Troy Driver Training | As Booked | N\A
Kate Brown Runnning | As Booked | N\A
Bahai Church | As Booked | N\A
Army Cadets | As Booked | N\A
Serenity Campers | As Booked | N\A
Fitzroy Fourbies | As Booked

## Tractor users
Name | trained | risk assesment completed
Scott Neill | Yes
Jim Wilson | Yes
Dion Cain | Yes
Tristan Watson | Yes
Dwayne Kersey | Yes
Troy Scharer | Yes
Kersey Snr | Yes

## Key Register
Name | Position | Keys
Scott Neill | DC | All

## Sheet1
Description | QTY | Shape | Size
10kms hr | 3 | as per picture attached | standard size?
Private Residence - No Scout Business | 1 | Square High VIS | 500 x 500mm
Utilities Gate Only | 1 | Square High VIS | 500 x 500mm
Seeonee Park is Private Property - No Access without permission - Park Contact: 0488008897 | 1 | Rectangle High Vis | 1000 x 500mm
MAP | 1 | Print? | 1800 x 1200mm
Brown Hut Arrow right | 2 | Rectangle | 500 x 200mm
Brown Hut Arrow Left | 3 | Rectangle | 500 x 200mm
Camp Petrel Arrow Right | 1 | Rectangle | 500 x 200mm
Camp Petrel Campsite | 1 | Rectangle | 500 x 200mm
Brown Hut Campsite | 1 | Rectangle | 500 x 200mm
Obstacle Course | 1 | Rectangle | 500 x 200mm

## Seeonee Pricing
Hiring agreement
Scout Camp | 7 | p/n
External Camp | 125 | day
day hire | 125
park access (per person day use only) | 2 | pp